## Master Task List
Task | Status | Date Added | Date Started | Date Completed | Notes | Phase | Task Start Date | Dev Priority
Add datastore Clear() overload fix | Pending | 2025-08-07 23:25 |  |  | Resolve error preventing class overload for Clear method | Development |  | Next
Change DB password handling. Review of the password generator | Complete | 2025-08-07 23:25 |  | 2025-08-08 | Refactor to avoid writing plaintext password to file; use memory until encrypted | Development |  | Next
Common password method (generation & reveal-once) | Pending | 2025-08-10 22:37 |  |  | Generator returns char[] only; enforce policy; reveal-once creates short-lived string for UI/copy then wipes. No plaintext bindings; clipboard warning. |  |  | Next
Early-logs pipeline (DPAPI .elog deferred inserts) | Active | 2025-08-10 22:37 | 2025-08-10 |  | Pre-login: write DPAPI-encrypted files containing parameterized INSERT templates (no plaintext payloads). On first successful login: decrypt, build JSON, encrypt with LogPayloadKey, bind params, execute via normal insert helper, batch per file. Quarantine on failure; secure-delete on success. Optional dedupe via LogGuid or hash of (CreatedUtc, EventCode, StackHash, SessionId). |  |  | Next
Finalize logging table schema | Complete | 2025-08-07 23:25 | 2025-08-10 | 2025-08-09 | Ensure all necessary columns and info are included Goal: Implement encrypted logging stored directly in the secure SQLCipher database, avoiding external log files. Criteria: - Dedicated `Logs` table in the encrypted DB with columns: Id (PK), Timestamp, Level, EventId, Area, Message, Tags. - All inserts go directly to the encrypted DB; no plaintext logs on disk. - Rotation handled via SQL (DELETE rows older than N days or exceeding N rows). - Logging disabled by default; enable through in-memory flag or encrypted config. - Optional export tool (dev-only) can SELECT from table and save to decrypted JSON or CSV. - Encrypted DB provides confidentiality; no separate AES encryption layer needed for log entries. Status: Pending. | Development |  | Next
Flip logging to LogPayloadKey | Complete | 2025-08-10 22:37 | 20250812 | 20250812 | Update encrypt/decrypt to pull LogPayloadKey from SecureEncryptedDataStore. Set PayloadFmt='json+aesgcm', PayloadVer=1, KeySetVersion=1. Maintain read support for any older machine-bound entries temporarily. |  |  | Next
Key provisioning component (DbPassword, LogPayloadKey, UserSecretsKey) | Active | 2025-08-10 22:37 | 20250812 |  | Create-if-missing and load into SecureEncryptedDataStore at startup; wipe temp buffers on all paths. No machine-binding. Integrate One-call Initialize(). |  |  | Next
Logs schema update (DROP+CREATE) | Complete | 2025-08-10 22:37 |  | 20250812 | Logs(Id PK, CreatedUtc INTEGER, Level CHECK, Source, EventCode, CorrelationId, SessionId, MachineId, AppVersion, IsCrash, Payload BLOB, PayloadFmt TEXT, PayloadVer INT, KeySetVersion INT, StackHash, Reserved1, Reserved2). Indexes on CreatedUtc, (Level,CreatedUtc), (EventCode,CreatedUtc), (SessionId,CreatedUtc), (IsCrash,CreatedUtc). |  |  | Next
Prep logging SQL scripts (no hardcoded SQL) | Pending | 2025-08-10 22:37 |  |  | Move all logging SQL into individual .sql files stored in encrypted 7z. Load via SecureEncryptedDataStore at runtime. Include flip-on scripts. |  |  | Next
Secure string handling improvements | Complete | 2025-08-07 23:25 |  | 2025-08-08 | Harden all string wipes using cryptographic RNG | Development |  | Next
Test export logic from encrypted DB | Complete | 2025-08-07 | 2025-08-09 | 2025-08-09 | Validate the export of the encrypted database tables before proceeding with other DB-related tasks. Goal: Enable a DEBUG-only hotkey to export encrypted DB without creating plaintext copies. Criteria: - Hotkey works only in DEBUG build (e.g., Ctrl+Alt+I). - Export directory auto-created: %LOCALAPPDATA%\MWPV\DebugExports\{yyyyMMdd-HHmm}. - DB copied as-is (encrypted) or packaged in password-protected 7z. - Manifest.json includes timestamp, version, schema version, file hash (no secrets). - Any generated passwords handled as char[], wiped after use. - No temp plaintext files; zero File.WriteAllText for sensitive data. Status: Pending. | Development |  | Next
Add Category UI redesign (inline overlay) | Pending | 2025-08-10 22:37 |  |  | Remove extra window; inline overlay in main panel. Duplicate validation in VM; data refresh unified. Sensitive inputs as char[]; wipe on cancel/save. |  |  | Soon
Memory Tracking & Shutdown Cleanup (planning) | Pending | 2025-08-10 22:37 |  |  | Design centralized memory tracker (register, wipe by label/category, wipe all). Plan normal and abnormal shutdown wipe sequences; integrate with SecureEncryptedDataStore. |  |  | Soon
Review main password entry/creation UI (visual + security) | Pending | 2025-08-10 22:37 |  |  | Fix spacing, alignment, visual hierarchy; ensure secure handling (no plaintext leaks). Make consistent with Add Category UI. |  |  | Soon
CategoryItemService planning | Pending | 2025-08-10 22:37 |  |  | Service boundary for Category Item CRUD; uses vw_CurrentPassword/vw_CurrentPin; all secrets as BLOBs with envelope; no plaintext bindings. |  |  | Later
Change Add Category method to overlay category list instead of separate UI | Pending | 2025-08-07 |  |  | Overlay appears when Add Category button is clicked; disappears when complete to reveal category list. Goal: Implement inline category add overlay, integrated with current data refresh logic. Criteria: - XAML overlay visibility bound to VM property (IsAddingCategory). - Duplicate category validation in VM with error feedback. - On save: add via service → panel updates source list → UI refresh. - Sensitive inputs handled with char[]; wiped on cancel/save. Status: Pending. | Development |  | Later
Design Category Item DataGrid for both editing existing items and creating new items | Pending | 2025-08-07 |  |  | Investigate whether to use the same DataGrid with logic to switch modes (edit vs. new) or separate grids for each. Decision required before implementation. | Development |  | Later
Design Category Item List Grid with buttons to open detail Category Item grid | Pending | 2025-08-07 |  |  | Grid mimics Category Grid layout but lists Category Items. Each row has a button to open the Category Item Detail DataGrid. Requires binding to results from the Category Item table. | Development |  | Later
Show selected category label on right-hand side before Add Category Item button | Pending | 2025-08-07 |  |  | Clicking a category button displays the category name as a label on the right side before the Add Category Item button. Requires binding. | Development |  | Later
Weekly review & diagrams (Sunday) | Pending | 2025-08-10 22:37 |  |  | Review tasks, schema, and security decisions; update master and daily lists. Regenerate big-picture diagrams (Setup, Category, CategoryItem) and security call map. |  |  | Recurring
1. Backend Code Documentation Plan (XML Comments) | Pending | 2025-08-07 |  |  |  | Documentation
1. Deployment Phase Planning | Pending | 2025-08-07 |  |  |  | Deployment
1. Secure Memory Tracker | Pending | 2025-08-07 |  |  |  | End-of-Dev
1.1 Prepare Final Installer | Pending | 2025-08-07 |  |  |  | Deployment
1.2 Code Signing | Pending | 2025-08-07 |  |  |  | Deployment
1.3 Build Download Web Page | Pending | 2025-08-07 |  |  |  | Deployment
1.4 Publish to Web | Pending | 2025-08-07 |  |  |  | Deployment
2. Feature Parking Lot (Future Enhancements) | Pending | 2025-08-07 |  |  |  | Deployment
2. Normal / Abnormal Shutdown Cleanup | Pending | 2025-08-07 |  |  |  | End-of-Dev
2. User-Level Documentation Plan | Pending | 2025-08-07 |  |  |  | Documentation
3. Inline Add Category UI Refactor | Pending | 2025-08-07 |  |  |  | Documentation
3. Secure Config File in Encrypted Key Archive | Pending | 2025-08-07 |  |  |  | End-of-Dev
4. Category Button Interaction Behavior | Pending | 2025-08-07 |  |  |  | Documentation
Abnormal Shutdown Tasks: | Pending | 2025-08-07 |  |  |  | End-of-Dev
Add Secure memory tracker and code to clear all secure memory items on exit | Pending | 2025-08-07 |  |  | Goal: Central registry to track/wipe sensitive buffers on demand for reuse in Security.Utility.dll. Criteria: - API supports: Register(buffer, label, category), TryWipe(label/category), WipeAll(). - Supports char[], byte[], SecureString. - Uses WeakReference to avoid extending object lifetimes. - Integration points: KeyPW, DB_Password, temp decrypt buffers. Status: Pending / optional. Goal: Ensure complete cleanup of sensitive data on both graceful and unexpected termination. Criteria: - Hooks in App.OnExit, Window.Closing, ProcessExit, UnhandledException. - Sequence: wipe UI controls, call SecureMemoryTracker.WipeAll(), close DB, flush logs. - Failsafe timer triggers wipe if main thread hangs. - Works when app is killed from Task Manager (within ProcessExit limits). Status: Pending.
Additional Notes / Future Enhancements | Pending | 2025-08-07 |  |  |  | End-of-Dev
Change Process: | Pending | 2025-08-07 |  |  |  | End-of-Dev
Examples of Stored Configs: | Pending | 2025-08-07 |  |  |  | End-of-Dev
File Format: | Pending | 2025-08-07 |  |  |  | End-of-Dev
Finalize Logging code changes to helper file | Pending | 2025-08-07 |  |  | (Same criteria as 'Finalize logging table schema' — ensure helper integration matches schema and security rules.)
Goal: | Pending | 2025-08-07 |  |  | Implement a centralized memory tracking system to register and monitor sensitive variables in memory during the application session. | End-of-Dev
Goal: | Pending | 2025-08-07 |  |  | Ensure complete cleanup of sensitive data during all types of shutdown (normal, crash, or forced exit). | End-of-Dev
Goal: | Pending | 2025-08-07 |  |  | Centralize all configurable app settings within the encrypted `.7z` archive (key file), ensuring tamper resistance and confidentiality. | End-of-Dev
Implementation Ideas: | Pending | 2025-08-07 |  |  |  | End-of-Dev
Key Features: | Pending | 2025-08-07 |  |  |  | End-of-Dev
Normal Shutdown Tasks: | Pending | 2025-08-07 |  |  |  | End-of-Dev
Security Features: | Pending | 2025-08-07 |  |  |  | End-of-Dev
Trigger Locations: | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Add hash/signature to config to detect tampering | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Allow user to adjust config values from within MWPV UI | Pending | 2025-08-07 |  |  |  | End-of-Dev
• App.OnExit() override | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Central WipeAll() method at shutdown. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Clear all registered sensitive entries from memory tracker. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• ClipboardClearDelay: seconds | Pending | 2025-08-07 |  |  |  | End-of-Dev
• DispatcherUnhandledException for WPF crashes | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Display full error dialog with stack trace (not just MessageBox). | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Global try/catch wrapping MainWindow execution | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Implement app-level lock screen triggered by inactivity | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Implement catch-all exception handling. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• InactivityTimeoutSeconds (e.g., 300) | Pending | 2025-08-07 |  |  |  | End-of-Dev
• JSON file (e.g., AppSettings.config.json) | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Load, deserialize, and edit in app | Pending | 2025-08-07 |  |  |  | End-of-Dev
• LockOnMinimize: true/false | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Only loaded during session | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Optional: Auto-expiry of memory entries after elapsed time. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Optionally log error in encrypted format. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Optionally require Windows Hello for modifying config | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Optionally version config files | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Rebuild and overwrite key.7z file with updated config | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Register all sensitive values (e.g., passwords, keys, decrypted values). | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Securely delete any decrypted temp files. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Skins: background color, button style | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Store references in a centralized SecureMemoryTracker class. | Pending | 2025-08-07 |  |  | Security Closeout Set | End-of-Dev
• Stored inside encrypted archive | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Support categorization (e.g., SessionBound, TempOnly). | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Tag variables with metadata like purpose or expiration. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Use WeakReference<T> or a secure dictionary. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Use Windows Hello to authenticate config changes | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Wipe DB password and any decrypted SQL. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Wipe all registered data during normal or abnormal shutdown. | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Wipe config from memory after use | Pending | 2025-08-07 |  |  |  | End-of-Dev
• Wipe sensitive memory and call shutdown cleanup logic. | Pending | 2025-08-07 |  |  |  | End-of-Dev